SCOPE OF WORK

FOR

ELECTRIC-POWERED WINGS SYSTEM (EPW) PROTOTYPE

Draft Version: 04

Date: 03 Feb 2026

OVERVIEW

- The Contractor is required to conduct research and development activities to design, build, and demonstrate a proof-of-concept personal Electric-Powered Wings System (EPW) that enables operator or skydiver to enhance horizontal aviation distance safely to ground.

BROAD SCOPE/TECHICAL APPROACHES

- The personal EPW system proof-of-concept will be developed through a phased approach:

  - Phase 1. The basic glider configuration (without engine), termed as the Glider Wing System, to establish technical feasibility of the aerofoil structural design, safety parameters, and human factors considerations. The Glider Wing System will consist of helmet, parachute, hands-free communications kit and telemetry sensors.

  - Phase 2. Design and integration of electric propulsion systems to achieve target EPW performance specifications, incorporating lessons learned and technical insights from Phase 1. The fabrication, assembly and testing of the EPW will be an option requirement after the successful outcome in the design analysis and establishment of the regulatory certifications required for the EPW.

REQUIREMENTS

- Task 1: System Design. The contractor shall conduct comprehensive performance analysis before prototyping, including flight dynamics with speed, altitude, and range calculations, endurance analysis based on battery capacity and power consumption, payload capacity assessment beyond pilot weight, weight distribution of the EPW, safety features, human factors engineering.

- It is recommended that to divide into 2 sub-tasks for progressive readiness to mitigate project development risks.

  - Task 1.1: Glider Wing System (Without engines). A lightweight, high-performance rigid wing system for human-flight glide without engines shall be first designed as the basis to design the EPW. This should include simulation and analysis to meet the specifications.

  - Task 1.2: Electric Powered Wings (EPW) System. The electric engines and batteries shall be integrated with the Glider Wing System to form the EPW System. The final design of the EPW System shall be based on the prototype and flight test performance of the Glider Wing System, refining the simulation and analysis.

- Task 2: Prototyping and Testing

  - Task 2.1: Prototyping and testing of Glider Wing System. Assembly of the sub-systems, integration of hardware and software components for the Glider Wing System will be done after the design and components selection are confirmed. Flight testing will progress systemically through wind tunnel testing to validate the performance against design specifications, before proceeding to live descents. The Contractor shall be responsible for getting the permits for live descents.

  - Task 2.2: Prototyping and testing of EPW System. The fabrication of the sub-systems, integration of hardware and software components for the EPW System will be done after the design is confirmed. The final live demonstration will be conducted by the Contractor to validate the performance against design specifications. The Contractor shall be responsible for getting the permits for live descents.

- Task 3: Data gathering for operators. Upon the successful completion of flight tests by the Contractor, at least two operators can be trained on the wingsuit and Glider Wing System to facilitate with the data gathering on the human factors and usability to improve the EPW design. The training for the operators will include mastering flight controls, high-altitude jump operations, opening sequence, landing approaches and emergency procedures.

SPECIFICATIONS OF GLIDER WING SYSTEM

- General Specifications. The Glider Wing System is capable to carry one personnel. The design shall make provision for the electric engines to be integrated in later phase of the project. The Glider Wing System will consist of helmet, parachute, hands-free communications kit and telemetry sensors. Any components shall integrate seamlessly with the EPW’s requirements.

  - Performance Specifications.

    - Max Take-off Weight:140kg (excluding payload)

    - Empty Weight: ≤ 45 kg

    - Pilot’s Weight: 80 to 95kg (Design point: 90kg)

    - Horizontal distance: More than 10 km (Exit altitude ≤ 5000m and parachute opening sequence at 1500m)

    - Optimal speed range: 170 to 230 km/h

    - Desired payload weight: ≤ 30kg including casing. (Demonstration may not include payload due to safety concerns.)

  - Size.

    - Operation: The wingspan is should not exceed 2.5m.

    - Storage: The wingspan is designed to packed to minimum size without affecting the operating structural integrity.

  - Others.

    - The Glider Wings shall be inherently stable in all flight modes or stability augmented.

    - Launching platform: Helicopter Airbus AS350 or equivalent.

    - All the parachute equipment and helmets are certified by aviation authorities and safe to use.

  - The final specifications shall be confirmed after the system design analysis.

SPECIFICATIONS OF EPW SYSTEM

- General Specifications. The EPW System is capable to carry one personnel. It will employ a Glide Wing System configuration powered by electric engines. The EPW System will include helmet, parachute, hands-free communications kit and telemetry sensors. Any components shall integrate seamlessly with the EPW’s requirements.

  - Performance Specifications.

    - Max Take-off Weight: 203kg (excluding payload)

    - Empty Weight: ≤ 108 kg

    - Pilot Weight: 80 to 95kg (Design point: 90kg)

    - Horizontal distance: More than 25 km (Exit altitude ≤ 5000m and parachute opening sequence at 1500m)

    - Optimal speed range: 170 to 230 km/h

    - Desired payload weight: ≤ 30kg including casing. (Demonstration may not include payload due to safety concerns.)

  - Size.

    - Operation: The wingspan is should not exceed 2.5m.

    - Storage: The wingspan is designed to packed to minimum size without affecting the operating structural integrity.

  - Others.

    - The Glider Wings shall be inherently stable in all flight modes or stability augmented.

    - Launching platform: Helicopter Airbus AS350 or equivalent.

    - All the parachute equipment and helmets are certified by aviation authorities and safe to use.

  - Ground Control Station (GCS). Datalink and communications between the pilot and the GCS are desired to maintain a stable communication link at line-of-sight distance of at least 5km away.

  - The final specifications shall be confirmed after the system design analysis.

DOCUMENTATION

- The following documentation listed in Table 2 shall be included as part of the project and shall include item identification data of all components.

Table 2: List of Documentation

| S/N | Publication Description |
| --- | --- |
| 1 | Operation Manual Includes operation, weight ranges, emergency procedures and troubleshooting of the EPW system. |
| 2 | Technical Documentation Includes safety analysis, blueprints, design drawings and test results |

SCHEDULE & DELIVERABLES

- The schedule and deliverables are shown in Table 3 below:

Table 3: Project Schedule

| Del No | Description of Deliverable | Schedule |
| --- | --- | --- |
| - | Contract Signing | T0 |
| 1 | Review Covering: - Design & analysis for Glider Wing System - Progress update on the EPW system | T0+3 |
| 2 | Review Covering: - Fabrication & Assembly of 1st Glider Wing System prototype - Prelim tunnel flight results for 1st Glider Wing System prototype - 1st data gathering and training on operators | T0+6 |
| 3 | Review Covering: - Updates on test & flight results of 1st Glider Wing System prototype - Fabrication & Assembly of 2nd Glider Wing System prototype | T0+9 |
| 4 | Review Covering: - Test & flight results of Glider Wing System - Design & analysis for EPW System | T0+12 |
| 5 | Review Covering: - Prelim tunnel flight results for EPW System prototype - 2nd data gathering and training on operators | T0+18 |
| 6 | Final Review Covering: - Performance Demo flights of EPW System - Completion of 2 Glider wing prototypes & 1 EPW System prototype | T0+24 |

T0: Start of contract

PAYMENT SCHEDULE

The payment for each deliverable should be commensurate with the completion of effort and resources required to achieve each deliverable.

| Del No | Schedule | Amount |
| --- | --- | --- |
| - | T0 |  |
| 1 | T0+3 |  |
| 2 | T0+6 |  |
| 3 | T0+9 |  |
| 4 | T0+12 |  |
| 5 | T0+18 |  |
| 6 | T0+24 |  |

Suggested equipment: Firebird Evo custom modification (with certifications) or equivalent. Main canopy = PD Pulse 260 or equivalent. Reserve canopy = PD Optimum 170 or equivalent. AAD = Vigil Cuatro or equivalent. Helmet: Tonfly TFX or equivalent.

Suggested equipment: Firebird Evo custom modification (with certifications) or equivalent. Main canopy = PD Pulse 260 or equivalent. Reserve canopy = PD Optimum 170 or equivalent. AAD = Vigil Cuatro or equivalent. Helmet: Tonfly TFX or equivalent.