## Feuille 1
DETAILED COSTS EXOWING PROJECT PHASE 1 Research & Development, 2x Prototype Exowing GLIDER Version, 2x 2 Students Training - duration 18 months PHASE 2 Research & Development, 1x Prototype Exowing EPW Version - duration 12 months OPTIONS Student Training Certification of Prototype Exowing GLIDER Series Exowing GLIDER Certification of Prototype Exowing EPW Series Exowing EPW Extra System - Landing Assist Extra System - Payload container Extra System - Flight data live helmet display Various Pilot's Equipment Spare Parts
|  | Designation | Provider | Price | Qty | Total | Repeat
T0 |  | PHASE 1 - Start = Contract signing | [8 empty] | A PAYER | PAYÉ
| 1 | Analysis & definition of project / Team management & Project organization |  |  |  | 198562.5 | 8675 | TASK 1.1 | 198562.5 |  | 18000
| 1.1 | Definition of needs and objectives / Hours | Exopter / E-Wings / APO / Atelier Aéronautique de Banneriau (AAB) | 162.5 | 240 | 39000 |  |  | 198562.5
| 1.2 | Feasibility study / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 140 | 22750
| 1.3 | Assessment of technical constraints + Requirements table / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 160 | 26000
| 1.4 | Team Management & project organization / Hours | Exopter / E-Wings / APO / NW | 137.5 | 155 | 21312.5 | 2612.5
| 1.5 | Airworthiness / Hours | Exopter / Velica | 212.5 | 80 | 17000 | 956.25 | TASK 4 & 7 |  |  |  | 5202.2
| 1.6 | Accounting - Bookkeeping - Regulation compliance / Hours | Arthae / Lamy-Lexel / Numans / Exopter | 137.5 | 140 | 19250 | 2543.75 |  |  |  |  | 4000
| 1.7 | Lawyers / Hours | Arthae / Lamy-Lexel | 250 | 80 | 20000 | 2031.25 |  |  |  | 12000 | 6000
| 1.8 | Intellectual Property / Hours | Arthae / Lamy-Lexel | 250 | 24 | 6000 | 531.25 |  |  |  | 3000
| 1.9 | Patent & Moral Rights research / Hours | Arthae / Lamy-Lexel | 250 | 12 | 3000 |  |  |  |  | 3000
| 1.10 | Singapore IP Office registration | Exopter / Singapore | 14625 | 1 | 14625 |  |  |  |  | ?
| 1.11 | Safety and Risk assessment | Exopter / E-Wings / APO | 137.5 | 70 | 9625 |  | TASK 2
| 2 | Aero Design of an Exowing - GLIDER version (GLD) |  |  |  | 199375 | 0 | TASK 3.1 | 199375 | 397937.5 | 45000 | 5000
| 2.1 | Aeronautical engineering & retro engineering + Aerodynamics + CFD simulations + Revisions | Exopter / E-Wings / APO / Atelier Aéronautique de Banneriau (AAB) | 187.5 | 640 | 120000 |  |  | 199375
| 2.2 | Creating plans and diagrams | Exopter / E-Wings / APO / AAB | 162.5 | 80 | 13000
| 2.3 | 3D modeling | Exopter / E-Wings / APO / AAB | 162.5 | 120 | 19500
| 2.4 | Designing wing Molds | Exopter / APO / AAB / C.Thebault | 162.5 | 80 | 13000
| 2.5 | Systems pre-integration | Exopter / E-Wings / APO / AAB | 162.5 | 80 | 13000
| 2.6 | Structural calculation | Exopter / APO / AAB | 162.5 | 120 | 19500
| 2.7 | drafting progress report | Exopter / E-Wings / APO / AAB | 137.5 | 10 | 1375
| 3 | Exowing Systems Design - GLIDER version (GLD) |  |  |  | 286813.5 | 0 | TASK 3.1 | 286813.5 | 684751 | 29500
| 3.1 | Jettison system of the Wing |  | 128835.5 |  |  |  |  | 286813.5
| 3.1.1 | Definition and analysis of Rescue parachute / Hours | Exopter / E-Wings / APO | 162.5 | 60 | 9750
| 3.1.2 | Study of a deployment POD and opening sequence for the Rescue parachute / Hours | Exopter / E-Wings / APO / Jim Parachutisme | 162.5 | 120 | 19500 |  |  |  |  | 2000
| 3.1.3 | Study of jettison Hook and jettison sequence / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 180 | 29250
| 3.1.4 | 3D modeling | Exopter / APO / AAB | 162.5 | 90 | 14625
| 3.1.5 | Production of prototype Hook | Exopter / APO / AAB | 4606 | 3 | 13818
| 3.1.6 | Tests & Analysis of Hook destruction - static test | Exopter / APO / AAB / AAPLUS | 162.5 | 80 | 13000
| 3.1.7 | Purchase & preparation of Rescue parachute | Expoter / Opales | 2353.75 | 3 | 7061.25 |  |  |  |  | 3000
| 3.1.8 | Tests & Analysis of Rescue parachute destruction incl. travel expenses France - Test bridge | Exopter / E-Wings / APO | 16556.25 | 1 | 16556.25 |  |  |  |  | 5000
| 3.1.9 | Modifications | Exopter / E-Wings / APO | 162.5 | 24 | 3900
| 3.1.10 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 3.2 | Attachment System - Pilot Seat |  | 68650
| 3.2.1 | Definition of a Pilot Seat and supports / Hours | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme | 162.5 | 120 | 19500
| 3.2.2 | Study of complete Seat Straps system for the main harness / Hours Jettisonable version | Exopter / E-Wings / APO / Jim Parachutisme / S.Zunino | 162.5 | 40 | 6500
| 3.2.3 | Analysis of Mass distribution + creation of Weight & Balance system / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 60 | 9750
| 3.2.4 | Angle of Attack (AOA) adjustement device / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 60 | 9750
| 3.2.5 | 3D modeling | Exopter / APO / AAB | 162.5 | 70 | 11375
| 3.2.6 | Test & Analysis | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.2.7 | Modification | Exopter / E-Wings / APO / AAB | 162.5 | 24 | 3900
| 3.2.8 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 3.3 | FDR (Flight Data Recorder) |  | 41350
| 3.3.1 | Definition of Hardware & Equipment / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 80 | 13000
| 3.3.2 | 3D modeling | Exopter / APO / AAB | 162.5 | 30 | 4875
| 3.3.3 | Integration of Probing devices on Exowing | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.3.4 | integration of a Data Management system | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.3.6 | Test & Analysis / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.3.7 | Modification | Exopter / E-Wings / APO / AAB | 162.5 | 16 | 2600
| 3.3.8 | Drafting of progress reports | Exopter / Ewing / APO | 137.5 | 10 | 1375
| 3.4 | Communication systems |  | 21978
| 3.4.1 | Study and intergration of Air to Air Bluetooth / DMC intercommunication | Exopter / E-Wings / APO | 162.5 | 20 | 3250
| 3.4.2 | Study and intergration of VHF radio Air to Air / Air to Ground communication | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.4.3 | procurement VHF and Cardo | Exopter / E-Wings / APO / AAB | 2403 | 1 | 2403
| 3.4.4 | Test & Analysis / Hours | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 3.4.5 | Modification | Exopter / E-Wings / APO / AAB | 162.5 | 12 | 1950
| 3.4.6 | drafting of progress reports | Exopter / E-wings / APO | 137.5 | 10 | 1375
| 3.5 | Payload pre design |  | 19500 | [6 empty] | 19500
| 3.5.1 | study of payload container, aerodynamic & structure, performance influence | Exopter / E-Wings / APO / AAB | 162.5 | 120 | 19500
| 3.6 | Intergration Approval Tests |  | 6500
| 3.6.1 | Integration tests of Dummy systems | Exopter / E-Wings / APO | 162.5 | 40 | 6500
| 4 | Parachute Design |  |  |  | 41943.75 | 0 | TASK 3.1 | 41943.75 | 726694.75 | 30000
| 4.1 | Definition and analysis of main parachute components (canopy, reserve, AAD, handles type and position) | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme / FireBird / Performance Design (PD) | 162.5 | 55 | 8937.5 |  |  | 41943.75
| 4.2 | Study of a specific opening sequence for the main parachute | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme / FireBird / PD | 162.5 | 38 | 6175
| 4.3 | Study of Cut-away sequence | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme / FireBird | 162.5 | 20 | 3250
| 4.4 | Parachute modifications | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme / FireBird | 162.5 | 80 | 13000
| 4.5 | Traval expenses to FireBird Workshop Germany - 2x 1 week | Exopter | 5956.25 | 1 | 5956.25
| 4.6 | Intergration of main parachute with Seat and Exowing | Exopter / E-Wings / APO / S.Zunino / Jim Parachutisme / FireBird | 162.5 | 20 | 3250
| 4.7 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 5 | Prototype Exowing GLD#1 production |  |  |  | 114067.5 | 0 | TASK 3.1 | 114067.5 | 840762.25 | 72200
| 5.1 | Wing Molds | C.Thebault / AAB / Exopter / APO | 12087.5 | 1 | 12087.5 |  |  | 114067.5 |  |  | 8000
| 5.2 | Wing Composite material + Assembly | C.Thebault / AAB / Exopter / APO | 25276.25 | 1 | 25276.25 |  |  |  |  | 20000
| 5.3 | Wing finishing & Painting | Exopter / APO | 3116.25 | 1 | 3116.25 |  |  |  |  | 2000
| 5.4 | Pilot Seat - Material + Assembly | C.Thebault / AAB / Exopter / APO | 9177.5 | 1 | 9177.5 |  |  |  |  | 10000
| 5.5 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / APO / AAB | 5073.75 | 1 | 5073.75 |  |  |  |  | 5000
| 5.6 | Parachute Harness production & modifications | FireBird | 15553.75 | 1 | 15553.75 |  |  |  |  | 10000
| 5.7 | Main Canopy + Reserve Canopy Purchase | Performance Design | 7230 | 1 | 7230 |  |  |  |  | 5000
| 5.8 | AAD Automatic Activation Device | Vigil AAD | 1688.75 | 1 | 1688.75 |  |  |  |  | 1600
| 5.9 | FDR Flight Data Recorder | Exopter / AAB / APO | 3587.5 | 1 | 3587.5 |  |  |  |  | 3500
| 5.10 | Communication systems | Exopter / AAB / APO | 2371.25 | 1 | 2371.25 |  |  |  |  | 2500
| 5.11 | Rescue parachute for Jettison procedure | Opale Parachutes | 1618.75 | 1 | 1618.75 |  |  |  |  | 1600
| 5.12 | Jettison system hardware | Exopter / APO | 4695 | 1 | 4695 |  |  |  |  | 1000
| 5.13 | Building a deployment POD, assembling and mounting of the rescue parachute | Jim Parachutisme | 1635 | 1 | 1635 |  |  |  |  | 1500
| 5.14 | Ground tests of attachment system and jettison procedures, integration and test of all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 32 | 5200
| 5.15 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600
| 5.16 | Transport case | Exopter / E-Wings / APO | 3863.75 | 1 | 3863.75 |  |  |  |  | 2000
| 5.17 | Onboard Camera | Gopro / insta | 612.5 | 2 | 1225 |  |  |  |  | 1500
| 5.18 | Operational spare parts Handles + Rescue + Reserve POD + Hardware | Exopter / E-wings / APO | 6692.5 | 1 | 6692.5 |  |  |  |  | 5000
| 5.19 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375 | [6 empty] | advance | M#1
MS#1 |  | T0+3 - MILESTONE #1 |  |  |  |  | 840762.25 | [5 empty] | 450000 | 390762.25
| 6 | Prototype Exowing GLD#1 Tunnel Tests |  |  |  | 78273.75 | 0 | TASK 3.2 | 78273.75 | 919036 | 15000
| 6.1 | Wind tunnel test - Private sessions - 20 hours Bovec, Slovenia | Inclined Lab AB / E-Wings / Aux Petits Oignons | 40388.75 | 1 | 40388.75 |  |  | 78273.75 |  | 10000
| 6.2 | Team travel + shipping equipment Bovec, Slovenia | Exopter / E-Wings / APO | 30822.5 | 1 | 30822.5 |  |  |  |  | 5000
| 6.3 | Analysis of Results and pre-flight Adjustments | Exopter / E-Wings / APO | 162.5 | 35 | 5687.5
| 6.4 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 7 | Singapore Team Training & Exowing Licence Examination |  |  |  | 131556 | 209829.75 | TASK 5 & 8 | 131556 | 131556 | 80000
| 7.1 | 1st wingsuit training august 2026 |  | 131556 | 1 | 131556 |  |  | 131556
MS#2 |  | T0+6 - MILESTONE #2 |  |  |  |  | 209829.75 |  |  |  | 354400
| 8 | Parachute flight Tests - 50 JMP / 2 WEEK |  |  |  | 40931.25 | 0 | TASK 3.2 | 40931.25 | 959967.25
| 8.1 | Jump Tickets + packing Airplane type : any skydiving airplane | Drop Zone | 53.75 | 50 | 2687.5 |  |  | 40931.25
| 8.2 | in-flight tests Team fares / Hours (incl. pilot + flight operator + engineer) | Exopter / E-Wings / APO | 187.5 | 120 | 22500
| 8.3 | Team Travel expenses to airfields + accommodation France | Exopter / E-Wings / APO | 8202.5 | 1 | 8202.5
| 8.4 | Analysis & Modification | Exopter / E-Wings / APO | 6166.25 | 1 | 6166.25
| 8.5 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 9 | Prototype Exowing GLD#1 1st Flight Tests - 10 FLT / 1 WEEK |  |  |  | 135230 | 0 | TASK 3.2 | 135230 | 1095197.25
| 9.1 | Test Pilot specific preliminary training Wind tunnel, Freefly, Wingsuit, Canopy piloting | Exopter | 5308.75 | 1 | 5308.75 |  |  | 135230
| 9.2 | Organization & Authorizations airspace, landing, coordination | Exopter / E-Wings / APO | 137.5 | 32 | 4400
| 9.3 | Aircraft rotations for in-flight tests + ground safety Airplane type Helicopter or back door airplane | Aircraft owner | 1130 | 10 | 11300
| 9.4 | in-flight tests Team fares / Hours (incl. pilot + flight operator + engineer) | Exopter / E-Wings / APO | 187.5 | 120 | 22500
| 9.5 | Travel expenses to airfields + Teams accommodation + System transport 1 week - France | Exopter / E-Wings / APO | 6516.25 | 1 | 6516.25
| 9.6 | Analysis of possible modifications and improvement for Prototype #2 | Exopter / E-Wings / APO / AAB | 162.5 | 24 | 3900
| 9.7 | Unscheduled mandatory modifications to systems | Exopter / E-Wings / APO | 8630 | 1 | 8630
| 9.8 | Aviation products operational liability insurance / per year | Exopter / MARSH | 35650 | 2 | 71300
| 9.9 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
MS#3 |  | T0+8 - MILESTONE #3 |  |  |  |  | 176161.25
| 10 | Prototype Exowing GLD#2 Production |  |  |  | 95287.5 | 95287.5 | TASK 3.2 | 95287.5 | 1190484.75 | 64700
| 10.1 | Wing Composite material + Assembly | C.Thebault / AAB / Exopter / APO | 25276.25 | 1 | 25276.25 |  |  | 95287.5 |  | 20000
| 10.2 | Wing Painting | Exopter / APO | 3116.25 | 1 | 3116.25 |  |  |  |  | 2000
| 10.3 | Pilot Seat - Material + Assembly | C.Thebault / AAB / Exopter / APO | 9177.5 | 1 | 9177.5 |  |  |  |  | 10000
| 10.4 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / APO / AAB | 5073.75 | 1 | 5073.75 |  |  |  |  | 5000
| 10.5 | Parachute Harness production & modifications | FireBird | 15553.75 | 1 | 15553.75 |  |  |  |  | 10000
| 10.6 | Main Canopy + Reserve Canopy Purchase | Performance Design | 7230 | 1 | 7230 |  |  |  |  | 5000
| 10.7 | AAD Automatic Activation Device | Vigil AAD | 1688.75 | 1 | 1688.75 |  |  |  |  | 1600
| 10.8 | FDR Flight Data Recorder | Exopter / AAB / APO | 3587.5 | 1 | 3587.5 |  |  |  |  | 3500
| 10.9 | Communication systems | Exopter / AAB / APO | 2371.25 | 1 | 2371.25 |  |  |  |  | 2500
| 10.10 | Rescue parachute for Jettison procedure | Opale Parachutes | 1618.75 | 1 | 1618.75 |  |  |  |  | 1600
| 10.11 | Jettison system hardware | Exopter / APO | 4695 | 1 | 4695
| 10.12 | Building a deployment POD, assembling and mounting of the rescue parachute | Jim Parachutisme | 1635 | 1 | 1635
| 10.13 | Ground tests of attachment system and jettison procedures, integration and test of all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 32 | 5200
| 10.14 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600
| 10.15 | Transport case | Exopter / E-Wings / APO | 3863.75 | 1 | 3863.75 |  |  |  |  | 2000
| 10.16 | Onboard Camera | Gopro | 612.5 | 2 | 1225 |  |  |  |  | 1500
| 10.17 | Drafting of progress report | Exopter / APO / AAB | 137.5 | 10 | 1375 | [6 empty] | M#3
MS#4 |  | T0+9 - MILESTONE #4 |  |  |  |  | 95287.5 |  |  |  |  | -95287.5 | 95287.5 | 0
| 11 | Prototype GLD#1 + GLD#2 Flight tests campaign #1 - 45 ROT / 3 WEEK - 2 PILOTS - 90 FLT |  |  |  | 166873.75 | 0 | TASK 3.2 | 166873.75 | 1357358.5
| 11.1 | Organization & Authorizations airspace, landing, coordination | Exopter / E-Wings / APO | 137.5 | 40 | 5500 |  |  | 166873.75
| 11.2 | Aircraft rotations for in-flight tests + ground safety Airplane type Helicopter or back door airplane | Aircraft owner | 1130 | 45 | 50850
| 11.3 | in-flight tests - Team fares / Hours (incl. pilots + flight operator + engineer) | Exopter / E-Wings / APO | 187.5 | 480 | 90000
| 11.4 | Travel expenses to airfields + Teams accommodation + System transport 3 weeks - France | Exopter / E-Wings / APO | 4216.25 | 3 | 12648.75
| 11.5 | Analysis of data and result assessment - Approval for Flight Tests Campaign #2 + Proto #2 et #3 | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 11.6 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
MS#5 |  | T0+12 - MILESTONE #5 |  |  |  |  | 166873.75 | [5 empty] | 166873.75
| 12 | Aero Design of an Exowing - Electric Powered version (EPW) |  |  |  | 462375 | 0 | TASK 1.2 | 462375 | 1819733.5 | 402000
| 12.1 | Aeronautical engineering & retro engineering + Aerodynamics + CFD simulations + Revisions | Exopter / E-Wings / APO / Atelier Aéronautique de Banneriau (AAB) | 187.5 | 600 | 112500 |  |  | 462375 |  | 60000
| 12.2 | Creating plans and diagrams | Exopter / E-Wings / APO / AAB | 162.5 | 120 | 19500
| 12.3 | 3D modeling | Exopter / E-Wings / APO / AAB | 162.5 | 190 | 30875
| 12.4 | Designing Molds | Exopter / APO / AAB / C.Thebault | 187.5 | 120 | 22500
| 12.5 | Creating custom fan + Engine upgrade | Exopter / AAB / APO | 187.5 | 630 | 118125 |  |  |  |  | 60000
| 12.6 | Creating custom pylon and nacelle | Exopter / AAB / APO | 187.5 | 120 | 22500
| 12.7 | Structural calculation | Exopter / APO / AAB | 187.5 | 160 | 30000
| 12.8 | Engine Control system | Exopter / APO / AAB | 187.5 | 160 | 30000 |  |  |  |  | 20000
| 12.9 | Custom Battery design + BMS + ESC pre-test / sizing / location | Exopter / APO / AAB | 187.5 | 240 | 45000 |  |  |  |  | 30000
| 12.10 | Systems pre-integration | Exopter / E-Wings / APO / AAB | 187.5 | 160 | 30000 |  |  |  |  | 20000
| 12.11 | drafting of progress report | Exopter | 137.5 | 10 | 1375
MS#6 |  | T0+14 - MILESTONE #6 |  |  |  |  | 462375 |  |  |  |  | -462375 | 462375
| 13 | Pilot Licence training program |  |  |  | 22790 | 0 | TASK 5 & 8 | 22790 | 1842523.5
| 12.1 | Elaborating training program | Exopter / E-Wings / APO | 137.5 | 150 | 20625 |  |  | 22790
| 12.2 | Hard & Soft copy of Pilot Licence training Program | Exopter / E-Wings / APO | 2165 | 1 | 2165
| 14 | Pilot Equipment Design and Procurement |  |  |  | 11091.5 | 7193.75 | TASK 3.1 | 19262 |  | 12000
| 13.1 | Definition and analysis of Main equipment components (suit, helmet, altimeters) | Exopter / E-Wings / APO | 137.5 | 4 | 550 |  |  | 19262
| 13.2 | Definition and analysis of Secondary equipment components (gloves, googles, thermal layers, hook knife) | Exopter / E-Wings / APO | 137.5 | 4 | 550
| 13.3 | Pilot main equipment components Procurement suit, helmet, altimeters | Exopter / E-Wings / APO | 3347 | 2 | 6694 | 5345
| 13.4 | Pilot secondary equipment components Procurement gloves, googles, thermal layers, hook knife | Exopter / E-Wings / APO | 786.25 | 2 | 1572.5 | 986.25
| 13.5 | Onboard Camera + mounts + integration + SD card | Gopro / insta | 862.5 | 2 | 1725 | 862.5
| 15 | Singapore Team Training & Exowing Licence Examination |  |  |  | 227088 | 0 | TASK 5 & 8 | 227088 | 2069611.5 | 200000
| 14.2 | 2nd Training - 4 to 5 weeks - MAY 2027 Wind Tunnel - Skydive with Wingsuit & Exowing Plane + Helicopter France - Sweden - Slovenia MAY 2027 | Exopter / E-Wings / APO | 227088 | 1 | 227088
|  | TOTAL PHASE 1 + TRAINING |  |  |  | 2212259
MS#7 |  | T0+15 - MILESTONE #7 |  |  |  |  | 260969.5 |  | 1371496.75
T1 |  | PHASE 2 - START T0+12
| 16 | ELECTRICAL CHAIN DESIGN, TESTING & PROTO APPROVAL |  |  |  | 207229 | 0 | TASK 6.1 | 207229 | 2276840.5
| 14.1 | Model DS-215-DIA HST (195 mm) Motor Type DSM 10066-290 controller MGM TMM 40063-3 X2-series - 4 x EDF + ESC x3-series + propellers (test bench) | Schuebler / APO / EXOPTER | 11504 | 4 | 46016 |  |  | 207229
| 14.2 | Building / testing custom Batteries + Charger | Shield Robotics / APO / EXOPTER | 58530 | 1 | 58530
| 14.3 | Pilot command, Controller, BMS, Wiring | Shield Robotics / APO / EXOPTER | 28802 | 1 | 28802
| 14.4 | Custom design Fan production + Adaptation to motor + Test CW / CCW | AAB / Schuebler / APO / EXOPTER | 46881 | 1 | 46881
| 14.5 | Test campaign | Exopter / E-Wings / APO | 187.5 | 144 | 27000
| 17 | Exowing PROTOTYPE EPW#1 production |  |  |  | 277130.5 | 217313.5 | TASK 6.1 | 277130.5 | 2553971
| 15.1 | Motorization for 1 system Model DS-215-DIA HST (195 mm) Motor Type DSM 10066-290 controller MGM TMM 40063-3 X2-series - 4 x EDF + ESC + propellers - 2 x spare propellers | Schuebler/ APO / EXOPTER | 11504 | 4 | 46016 | 46016 |  | 277130.5
| 15.2 | Custom fan molds CW & CCW | C.Thebault / AAB / Exopter / APO | 10870 | 2 | 21740
| 15.3 | Custom fan material + assembly | C.Thebault / AAB / Exopter / APO | 15760 | 1 | 15760 | 15760
| 15.4 | Batteries 2 x sets of custom batteries for 14S EDF | AAB / APO / EXOPTER | 30000 | 2 | 60000 | 60000
| 15.5 | Electronics & Wiring | Exopter / APO / Shield Robotics | 6922 | 1 | 6922
| 15.6 | Wing Molds | C.Thebault / AAB / Exopter / APO | 22087.5 | 1 | 22087.5
| 15.7 | Wing Composite material + Assembly | C.Thebault / AAB / Exopter / APO | 25276.25 | 1 | 25276.25 | 25276.25
| 15.8 | Wing finishing & Painting | Exopter / APO | 3116.25 | 1 | 3116.25 | 3116.25
| 15.9 | Pilot Seat - Material + Assembly | C.Thebault / AAB / Exopter / APO | 9177.5 | 1 | 9177.5 | 9177.5
| 15.10 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / APO / AAB | 5073.75 | 1 | 5073.75 | 5073.75
| 15.11 | Parachute Harness production & modifications | FireBird | 15553.75 | 1 | 15553.75 | 15553.75
| 15.12 | Main Canopy + Reserve Canopy Purchase | Performance Design | 7230 | 1 | 7230 | 7230
| 15.13 | AAD Automatic Activation Device | Vigil AAD | 1688.75 | 1 | 1688.75 | 1688.75
| 15.14 | FDR Flight Data Recorder | Exopter / AAB / APO | 3587.5 | 1 | 3587.5 | 3587.5
| 15.15 | Communication systems | Exopter / AAB / APO | 2371.25 | 1 | 2371.25 | 2371.25
| 15.16 | Rescue parachute for Jettison procedure | Opale Parachutes | 1618.75 | 1 | 1618.75 | 1618.75
| 15.17 | Jettison system hardware | Exopter / APO | 4695 | 1 | 4695 | 4695
| 15.18 | Building a deployment POD, assembling and mounting of the rescue parachute | Jim Parachutisme | 1635 | 1 | 1635 | 1635
| 15.19 | Ground tests of attachment system and jettison procedures, integration and test of all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 42 | 6825 | 6825
| 15.20 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600 | 2600
| 15.21 | Transport case | Exopter / E-Wings / APO | 3863.75 | 1 | 3863.75 | 3863.75
| 15.22 | Onboard Camera | Gopro / insta | 612.5 | 2 | 1225 | 1225
| 15.23 | Operational spare parts - Handles + Rescue + Reserve POD + Hardware | Exopter / E-wings / APO | 7692.5 | 1 | 7692.5
| 15.24 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
MS#8 |  | TO+18 MILESTONE #8 |  |  |  |  | 484359.5
| 18 | Exowing PROTOTYPE EPW#1 Tunnel Tests |  |  |  | 78273.75 | 0 | TASK 6.2 | 78273.75 | 2632244.75
| 16.1 | Wind tunnel test - Private sessions - 20 hours Stockholm, Sweden | Inclined Lab AB / E-Wings / Aux Petits Oignons | 40388.75 | 1 | 40388.75 |  |  | 78273.75
| 16.2 | Team travel + shipping equipment Stockholm, Sweden | Exopter / E-Wings / APO | 30822.5 | 1 | 30822.5
| 16.3 | Analysis of Results and pre-flight Adjustments | Exopter / E-Wings / APO | 162.5 | 35 | 5687.5
| 16.4 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 19 | Parachute flight Tests |  |  |  | 20465.625 | 0 | TASK 6.2 | 20465.625 | 2652710.375
| 17.1 | Jump Tickets + packing Airplane type : any skydiving airplane | Drop Zone | 53.75 | 25 | 1343.75 |  |  | 20465.625
| 17.2 | in-flight tests Team fares / Hours (incl. pilot + flight operators + engineers) | Exopter / E-Wings / APO | 187.5 | 60 | 11250
| 17.3 | Team Travel expenses to airfields + accommodation France | Exopter / E-Wings / APO | 4101.25 | 1 | 4101.25
| 17.4 | Analysis & Modification | Exopter / E-Wings / APO | 3083.125 | 1 | 3083.125
| 17.5 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 5 | 687.5
MS#9 |  | TO+21 MILESTONE #9 |  |  |  |  | 98739.375
| 20 | Exowing EPW#1 + GLD#1 Flight tests campaign #2 - 45 ROT / 3 WEEK |  |  |  | 166873.75 | 0 | TASK 6.2 | 166873.75 | 2819584.125
| 18.1 | Organization & Authorizations airspace, landing, coordination | Exopter / E-Wings / APO | 137.5 | 40 | 5500 |  |  | 166873.75
| 18.2 | Aircraft rotations for in-flight tests + ground safety Airplane type Helicopter or back door airplane | Aircraft owner | 1130 | 45 | 50850
| 18.3 | in-flight tests - Team fares / Hours (incl. pilot + flight operators + engineers) | Exopter / E-Wings / APO | 187.5 | 480 | 90000
| 18.4 | Travel expenses to airfields + Teams accommodation + System transport 3 weeks - France | Exopter / E-Wings / APO | 4216.25 | 3 | 12648.75
| 18.5 | Analysis of data and result assessment | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 18.6 | Drafting of progress reports | Exopter / E-Wings / APO | 137.5 | 10 | 1375
| 21 | Acceptance tests - Official performance demonstration |  |  |  | 36612.5 | 11119.375 | TASK 5 & 8 | 36612.5
| 19.1 | 1 week - All completed Exowing tests | Exopter / E-Wings / APO / Singapore Team | 34540 | 1 | 34540 | 8541.25 |  | 36612.5
| 19.2 | Performance flight by an Exowing instructor | Exopter / E-Wings / APO | 2072.5 | 1 | 2072.5 | 2578.125
MS#10 |  | T0+24 - MILESTONE #10 |  |  |  |  | 203486.25
T1+12 |  | TOTAL PHASE 2 |  |  |  | 786585.125 |  |  | 3579219
T0+24 |  | TOTAL PHASE 1 + PHASE 2 + TRAINING |  |  |  | 2998844.125 |  | SOMME MILESTONES | 2998844.125 | OK
OPTIONS
| 20 | Singapore Team Training - Extra pilots on planned Trainings |  |  |  | 191771 | 0 | TASK 5 & 8 | 191771 | 191771
| 20.1 | 1st Extra Pilot (3 pilots total) - Wingsuit training - 5 weeks - August / September 2026 | Exopter / E-Wings / APO | 53260 | 1 | 53260
| 20.2 | 2nd Extra Pilot (4 pilots total) - Wingsuit training - 5 weeks - August / September 2026 | Exopter / E-Wings / APO | 26189 | 1 | 26189 |  |  | 79449
| 20.3 | 1st Extra Pilot (3 pilots total) - 2nd Training - 5 weeks - May 2027 Wind Tunnel - Skydive with Wingsuit & Exowing Plane + Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO / Savoie Hélicoptère | 74639 | 1 | 74639
| 20.4 | 2nd Extra Pilot (4 pilots total) - 2nd Training - 5 weeks - May 2027 Wind Tunnel - Skydive with Wingsuit & Exowing Plane + Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO / Savoie Hélicoptère | 37683 | 1 | 37683 |  |  | 112322
| 21 | Singapore Team Extra Training & Exowing Licence Examination |  |  |  | 339281 | 0 | TASK 5 & 8 | 339281 | 339281
| 21.1 | 1st Pilot Training - 5 weeks - MAY 2028 / 2029 Wind Tunnel - Skydive with Exowing Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO | 170890 | 1 | 170890
| 21.2 | 2nd Pilot Training - 5 weeks - MAY 2028 / 2029 Wind Tunnel - Skydive with Exowing Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO | 56069 | 1 | 56069
| 21.3 | 3rd Pilot Training - 5 weeks - MAY 2028 / 2029 Wind Tunnel - Skydive with Exowing Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO | 74639 | 1 | 74639
| 14.2 | 4th Pilot Training - 5 weeks - MAY 2028 / 2029 Wind Tunnel - Skydive with Exowing Helicopter France - Sweden - Slovenia | Exopter / E-Wings / APO | 37683 | 1 | 37683
| 22 | Certification of Exowing GLD - Compliance & Quality inspection Wing + Systems + Equipment - Use of GLD#2 as sample |  |  | 1 | 173365.25 |  | TASK 4 & 7 | 173365.25
| 22.1 | Production of Exowing GLD#3 | C.Thebault / SC Aero / AAB / Exopter / APO | 57056.25 | 1 | 57056.25
| 22.2 | Electro Magnetic Compatibility / EMI | Exopter / tektronix | 30471 | 1 | 30471 |  |  | 0
| 22.3 | Environemental worthiness tests MIL-STD-810G Destruction of Exowing GLD#2 | Exopter / Applus | 65250 | 1 | 65250
| 22.4 | Analysis of data and result assessment - Certification of Exowing GLD#1 + GLD#3 + All future Exowing GLD | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 22.5 | Flight certification / Airworthiness approval | Exopter / Velica | 7213 | 1 | 7213
| 22.6 | Drafting of progress report & Documentation | Exopter / E-Wings / APO | 137.5 | 50 | 6875
| 23 | Exowing SERIES GLD PRODUCTION |  |  |  | 105203.5 |  | TASK 3.2 | 105203.5
| 23.1 | Wing Molds preparation and calibration | C.Thebault / SC Aero / AAB / Exopter / APO | 6275 | 1 | 6275 |  |  | 105203.5
| 23.2 | Wing Composite material + Assembly | C.Thebault / AAB / Exopter / APO | 25276.25 | 1 | 25276.25
| 23.3 | Wing Painting | Exopter / APO | 3116.25 | 1 | 3116.25
| 23.4 | Pilot Seat - Material + Assembly | C.Thebault / AAB / Exopter / APO | 9177.5 | 1 | 9177.5
| 23.5 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / APO / AAB | 5073.75 | 1 | 5073.75
| 23.6 | Parachute Harness production | FireBird | 15553.75 | 1 | 15553.75
| 23.7 | Main Canopy + Reserve Canopy Purchase | Performance Design | 7230 | 1 | 7230
| 23.8 | AAD Automatic Activation Device | Vigil AAD | 1688.75 | 1 | 1688.75
| 23.9 | FDR Flight Data Recorder | Exopter / AAB / APO | 3587.5 | 1 | 3587.5
| 23.10 | Communication systems | Exopter / AAB / APO | 2371.25 | 1 | 2371.25
| 23.11 | Rescue parachute for Jettison procedure | Opale Parachutes | 1618.75 | 1 | 1618.75
| 23.12 | Jettison system hardware | Exopter / APO | 4695 | 1 | 4695
| 23.13 | Building a deployment POD, assembling and mounting of the rescue parachute | Jim Parachutisme | 1635 | 1 | 1635
| 23.14 | Ground tests of attachment system and jettison procedures, integration and test of all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 32 | 5200
| 23.15 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600
| 23.16 | Transport case | Exopter / E-Wings / APO | 3863.75 | 1 | 3863.75
| 23.17 | In-Flight Tests & Analysis of Results - 2 FLT | Exopter / APO / AAB | 4863 | 1 | 4863
| 23.18 | Documentation |  | 1378 | 1 | 1378
| 24 | Certification of Exowing EPW - Compliance & Quality inspection Wing + Engines + Batteries + Systems + Equipment - Use of EPW#1 as sample |  |  | 1 | 363622.5 |  | TASK 4 & 7 | 363622.5
| 24.1 | Production of Exowing EPW#2 | C.Thebault / SC Aero / AAB / Exopter / APO | 217313.5 | 1 | 217313.5
| 24.2 | Electro Magnetic Compatibility EMC / EMI | Exopter / tektronix | 60471 | 1 | 60471 |  |  | 0
| 24.3 | Compliance Batteries | shield robotics/APO/EWING/EXOPTER
| 24.4 | Compliance EDF | schuebler/ APO / EXOPTER
| 24.5 | Environemental worthiness tests MIL-STD-810G Destruction of Exowing EPW#1 | Exopter / Applus | 65250 | 1 | 65250
| 24.6 | Flight certification / Airworthiness approval | Exopter / Velica | 7213 | 1 | 7213
| 24.7 | Analysis of data and result assessment - Certification of Exowing EPW#2 + All future EPW | Exopter / E-Wings / APO / AAB | 162.5 | 40 | 6500
| 24.8 | Drafting of progress report & Documentation | Exopter / E-Wings / APO | 137.5 | 50 | 6875
| 25 | Exowing SERIES EPW production |  |  |  | 209743.5 | 186088.5 | TASK 6.1 | 209743.5 | 209743.5
| 25.1 | Motorization for 1 system Model DS-215-DIA HST (195 mm) Motor Type DSM 10066-290 controller MGM TMM 40063-3 X2-series - 4 x EDF + ESC + propellers - 2 x spare propellers | Schuebler/ APO / EXOPTER | 11504 | 4 | 46016 | 46016 |  | 209743.5
| 25.2 | Custom fan molds CW & CCW preparation and calibration | C.Thebault / AAB / Exopter / APO | 3872 | 1 | 3872
| 25.3 | Custom fan material + assembly | C.Thebault / AAB / Exopter / APO | 15760 | 1 | 15760 | 15760
| 25.4 | Batteries 1 x set of custom batteries for 14S EDF | AAB / APO / EXOPTER | 30000 | 1 | 30000 | 30000
| 25.5 | Electronics & Wiring | Exopter / APO / Shield Robotics | 6922 | 1 | 6922
| 25.6 | Wing Molds preparation and calibration | C.Thebault / AAB / Exopter / APO | 6275 | 1 | 6275
| 25.7 | Wing Composite material + Assembly | C.Thebault / AAB / Exopter / APO | 25276.25 | 1 | 25276.25 | 25276.25
| 25.8 | Wing finishing & Painting | Exopter / APO | 3116.25 | 1 | 3116.25 | 3116.25
| 25.9 | Pilot Seat - Material + Assembly | C.Thebault / AAB / Exopter / APO | 9177.5 | 1 | 9177.5 | 9177.5
| 25.10 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / APO / AAB | 5073.75 | 1 | 5073.75 | 5073.75
| 25.11 | Parachute Harness production & modifications | FireBird | 15553.75 | 1 | 15553.75 | 15553.75
| 25.12 | Main Canopy + Reserve Canopy Purchase | Performance Design | 7230 | 1 | 7230 | 7230
| 25.13 | AAD Automatic Activation Device | Vigil AAD | 1688.75 | 1 | 1688.75 | 1688.75
| 25.14 | FDR Flight Data Recorder | Exopter / AAB / APO | 3587.5 | 1 | 3587.5 | 3587.5
| 25.15 | Communication systems | Exopter / AAB / APO | 2371.25 | 1 | 2371.25 | 2371.25
| 25.16 | Rescue parachute for Jettison procedure | Opale Parachutes | 1618.75 | 1 | 1618.75 | 1618.75
| 25.17 | Jettison system hardware | Exopter / APO | 4695 | 1 | 4695 | 4695
| 25.18 | Building a deployment POD, assembling and mounting of the rescue parachute | Jim Parachutisme / Zunino | 1635 | 1 | 1635 | 1635
| 25.19 | Ground tests of attachment system and jettison procedures, integration and test of all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 42 | 6825 | 6825
| 25.20 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600 | 2600
| 25.21 | Transport case | Exopter / E-Wings / APO | 3863.75 | 1 | 3863.75 | 3863.75
| 25.22 | In-Flight Tests & Analysis of Results - 2 FLT | Exopter / APO / AAB | 4863 | 1 | 4863
| 25.23 | Documentation | Exopter | 1723 | 1 | 1723
| 26 | integration of information display |  |  |  | 8423
| 26.1 | Helmet stereoscopic data display / per helmet Modular configuration, including air speed, glide, height, compass, destination heading, artificial horizon, battery endurance and power, alarms, TCAS with other pilots. | Exopter / APO / E-Wings | 6285 | 1 | 6285
| 26.2 | Documentation | Exopter | 2138 | 1 | 2138
| 27 | Payload Container Production + 10 Flights test |  |  |  | 113008.25
| 27.1 | Production of payload container following previous design + Operationnal adjustments Carbon mold, materials, work hours, attachement and cut-away system | Exopter / E-Wings / APO / AAB | 36250 | 1 | 36250
| 27.2 | Ground tests of attachment system and jettison procedures, integration and test with all systems (incl. pilot + flight operator) | Exopter / E-Wings / APO | 162.5 | 64 | 10400 | 10400
| 27.3 | Basic tests to validate mechanical aspects | Exopter / E-Wings / APO | 162.5 | 16 | 2600 | 2600
| 27.4 | Organization & Authorizations airspace, landing, coordination | Exopter / E-Wings / APO | 137.5 | 32 | 4400
| 27.5 | Aircraft rotations for in-flight tests + ground safety Airplane type Helicopter or back door airplane | Aircraft owner | 1130 | 10 | 11300
| 27.6 | in-flight tests Team fares / Hours (incl. pilot + flight operator + engineer) | Exopter / E-Wings / APO | 187.5 | 120 | 22500
| 27.7 | Travel expenses to airfields + Teams accommodation + System transport 1 week - France | Exopter / E-Wings / APO | 6516.25 | 1 | 6516.25
| 27.8 | Analysis of possible modifications and improvement for Payload version #2 | Exopter / E-Wings / APO / AAB | 162.5 | 24 | 3900
| 27.9 | Unscheduled mandatory modifications to systems | Exopter / E-Wings / APO | 8630 | 1 | 8630
| 27.10 | Aviation products operational liability insurance / per year | Exopter / MARSH | 3762 | 1 | 3762
| 27.11 | Drafting of progress reports & Documentation | Exopter / E-Wings / APO | 137.5 | 20 | 2750
| 28 | Landing assistance system |  |  |  | 450000
| 28.1 | Analysis, Design, Production, and test of a Landing Assistance system allowing Exowing EPW to land with reasonnable weight supported by pilot. Technology may vary according to discussion with User, Pilots, and feasibility | Exopter / APO / AAB / Shield Robotics | 450000 | 1 | 450000
| 29 | Operational spare parts
| 29.1 | Hook - Material + Assembly of a complete attachment system between Wings and Pilot Seat | Exopter / E-wings / APO
| 29.2 | Exowing Jettison handle
| 29.3 | Main Canopy - Fire Bird Custom made
| 29.4 | Reserve Canopy - Fire Bird "Rush" certified canopy
| 29.5 | Reserve POD + Pilot Chute
| 29.6 | Parachute main harness rig - Fire Bird "Evo" Custom made
| 29.7 | Pilot Chute + Bridle + Spring system
| 29.8 | OTS (Over the Shoulder) handles - Left and Right (2 handles)
| 29.9 | Parachute Cutaway + Reserve handles (2 handles)
| 29.10 | AAD Automatic Activation Device
| 29.11 | Rescue parachute for Jettison procedure
| 29.12 | Fin / Vertical Stabilizer - Left or Right side
| 29.13 | Seat custom padding
| 29.14 | Seat Straps + Buckles - Complete set
| 30 | Pilot Equipment | [5 empty] | TASK 3.1 | 19262
| 30.1 | Pilot suit - Custom made Freefly or Wind-tunnel type | Tonfly | 1685 | 1 | 1685 |  |  | 19262
| 30.2 | Pilot Helmet - Custom made TFX Tonfly | Tonfly | 1230 | 1 | 1230
| 30.3 | Onboard Camera + mounts + integration + SD card | Gopro / insta | 862.5 | 1 | 862.5 | 862.5
| 31 | Shipping |  |  |  | 48475 | 6423.75 |  | 48475
| 31.1 | Transport from France to Singapore + Insurance / per complete Exowing systems | Fedex / Exopter | 6423.75 | 4 | 25695 | 6423.75 |  | 48475
| 31.2 | Team Travel Expenses | Airline / Exopter | 22780 | 1 | 22780
| 32 | MAINTENANCE |  |  |  | 9107 | 0 |  | 9107
| 16.9 | Spare Parts for Jettison and Cut-away - main canopy + emergency handles + reserve POD | FireBird / Performance Design | 3762 | 1 | 3762
| 16.20 | Pilot main equipment Procurement suit, helmet, altimeters | Exopter / E-Wings / APO | 5345 | 1 | 5345
| 16.21 | Pilot secondary equipment Procurement gloves, googles, thermal layers, hook knife | Exopter / E-Wings / APO | 986.25 | 1 | 986.25