## Feuille 1
DETAILED COSTS EXOWING PROJECT PHASE 1 Research & Development, 2x Prototype Exowing GLIDER Version, 2x 2 Students Training PHASE 2 Research & Development, 1x Prototype Exowing EPW Version OPTIONS (ANNEX) Extra Pilot Extra Training Certification of Prototype Exowing GLIDER Series Exowing GLIDER Certification of Prototype Exowing EPW Series Exowing EPW Extra System - Landing Assist Extra System - Payload container Extra System - Flight data live helmet display Various Pilot's Equipment Spare Parts
| Designation | Price | SGP REF
| PHASE 1 - Start = Contract signing + advance payment | 350000
1 | Analysis & definition of project / Team management & Project organization Includes : Safety and Risk Assessment - Analysis of system hazard and safety for all phases of operations + Safety Assessment Report Includes : Airworthiness Certification + Compliance and Environmental Pre-Certification | 198562.5 | TASK 1.1
2 | Aero Design of an Exowing - GLIDER version (GLD) | 199375 | TASK 1.1
3 | Exowing Systems Design - GLIDER version (GLD) | 286813.5 | TASK 1.1
3.1 | Jettison system of the Wing | 128835.5
3.2 | Attachment System - Pilot Seat | 68650
3.3 | FDR (Flight Data Recorder) | 41350
3.4 | Communication systems | 21978
3.5 | Payload pre-design | 19500
3.6 | Intergration Approval Tests | 6500
4 | Parachute Design | 41943.75 | TASK 1.1
5 | Prototype Exowing GLD#1 production | 114067.5 | TASK 2.1
6 | Prototype Exowing GLD#1 Tunnel Tests | 78273.75 | TASK 2.1
| T0+3 - MILESTONE #1 | 919036
7 | Singapore Team Training & Exowing Licence Examination | 131556 | TASK 3
8 | Parachute flight Tests - 50 JMP / 2 WEEK | 40931.25 | TASK 2.1
9 | Prototype Exowing GLD#1 1st Flight Tests - 10 FLT / 1 WEEK | 135230 | TASK 2.1
10 | Prototype Exowing GLD#2 Production | 95287.5 | TASK 2.1
11 | Prototype GLD#1 + GLD#2 Flight tests campaign #1 - 45 ROT / 3 WEEK - 2 PILOTS - 90 FLT | 166873.75 | TASK 2.1
| T0+6 - MILESTONE #2 | 569878.5
12 | Aero Design of an Exowing - Electric Powered version (EPW) | 462375 | TASK 1.2
| T0+10 - MILESTONE #3 | 462375
13 | Pilot Licence training program | 22790 | TASK 3
14 | Pilot Equipment Design and Procurement | 11091.5 | TASK 3
15 | Singapore Team Training & Exowing Licence Examination | 227088 | TASK 3
| T0+15 - MILESTONE #4 | 260969.5
| TOTAL PHASE 1 + TRAINING | 2212259
PHASE 2 - START T0+12
16 | Electrical Chain Design, Testing & Prototype Approval | 207229 | TASK 2.2
17 | Prototype Exowing EPW#1 production | 277130.5 | TASK 2.2
| TO+18 MILESTONE #5 | 484359.5
18 | Prototype Exowing EPW#1 Tunnel Tests | 78273.75 | TASK 2.2
19 | Parachute flight Tests | 20465.63 | TASK 2.2
20 | Exowing EPW#1 + GLD#1 Flight tests campaign #2 - 45 ROT / 3 WEEK | 166873.75 | TASK 2.2
21 | Acceptance tests - Official performance demonstration | 36612.5 | TASK 2.1 TASK 2.2 TASK 3
| T0+24 - MILESTONE #6 | 302225.63
| TOTAL PHASE 2 | 786585.13
| TOTAL PHASE 1 + PHASE 2 + TRAINING | 2998844.13