## Feuille 1
DETAILED COSTS EXOWING PROJECT PHASE 1 Research & Development, 2x Prototype Exowing GLIDER Version, 2x 2 Students Training PHASE 2 Research & Development, 1x Prototype Exowing EPW Version OPTIONS (ANNEX) Extra Pilot Extra Training Certification of Prototype Exowing GLIDER Series Exowing GLIDER Certification of Prototype Exowing EPW Series Exowing EPW Extra System - Landing Assist Extra System - Payload container Extra System - Flight data live helmet display Various Pilot's Equipment Spare Parts
| Designation | prix (coutant) | dû | main d oeuvre | Presta Matt Blond (net) | devis | details
1 | Analysis & definition of project / Team management & Project organization Includes : Safety and Risk Assessment - Analysis of system hazard and safety for all phases of operations + Safety Assessment Report Includes : Airworthiness Certification + Compliance and Environmental Pre-Certification | 25000 |  |  | 12500 x 2 = 25000
2 | Exowing Aero Design - GLIDER version (GLD) | 10000 | 50000 |  | 12500 x 2 = 25000
3 | Exowing Systems Design - GLIDER version (GLD) | 16500
3.1 | Jettison system of the Wing | 10000
3.2 | Attachment System - Pilot Seat
3.3 | FDR (Flight Data Recorder) | 1500 |  |  |  |  | air data + imu + gps + sd + display + hardware
3.4 | Communication systems | 2000 |  |  |  |  | icom + oreillette + ptt
3.5 | Payload pre-design | 3000
3.6 | Intergration Approval Tests
4 | Parachute Design and production proto#1 | 30000 |  |  | 5000 |  | devis a vallider avec Fire bird + transport hebergement en allemagne dev 12000 + 7000/sac + declencheur x2 3000
5 | Prototype Exowing GLD#1 production | 6000 |  |  |  |  | 2mois et demi 2 personne 400/jour + materiel
6 | Prototype Exowing GLD#1 Tunnel Tests | 7000 |  |  | 7jours x2 |  | hebergement +trajet+heure de tunnel et 6H aile et 3H WS
7 | Parachute flight Tests - 50 JMP / 2 WEEK | 4000 |  |  | 14 jours |  | ticket + hebergement transport
8 | Pilot Equipment Design and Procurement per Pilot | 10000 |  |  |  | a faire | casque + combi + SV technique + gants + chaussures (ete/hiver) pour 1 personne ?
GLD#1 system production
| tunnel warm up and validation for the sky | 5000
9 | Prototype Exowing GLD#1 1st Flight Tests - 20 FLT / 2 WEEK | 25000 |  |  |  |  | 1000euros/rotation + 5000 par semaine
10 | Exowing Aero Design - Electric Powered Wing EDF + JET + Bicopter | 20000 |  |  | 15 jours x 2 |  | nouvelle repartition structurelle + amelioration technique de fabrication + moules suplementaire
11 | Electrical Chain Design, Testing & Prototype Approval | 5000 |  |  |  |  | utilisation du module ewing - bilan et etat de service
12 | Prototype Exowing EPW#1 production - version EDF 145mm | 7000 |  |  | 50 jours
13 | Exowing Systems Design - EPW version (EDF) | 25000
14 | Production module Bicopter | 10000
15 | Prototype Exowing EPW#1 Tunnel Tests | 10000 |  |  | 7 jours x2
16 | Parachute EPW/JPW Design and production proto#2 | 25000 |  |  | 7 jours
17 | Parachute EPW/JPW Flight Tests | 4000 |  |  | 14 jours |  | gros sac avec mousse pour voler en mode glider
18 | Prototype Exowing EPW#1 (EDF mode) 1st Flight Tests - 10 FLT / 1 WEEK | 15000 |  |  | 7 jours x2 |  | 1000euros/rotation + 5000 par semaine
19 | Prototype Exowing EPW#1 (Bicopter mode) 1st Flight Tests - 10 FLT / 1 WEEK | 15000 |  |  | 7 jours x2 |  | 1000euros/rotation + 5000 par semaine
20 | GLD#1 + EPW#1 (GLD mode) Flight tests campaign #2 - 45 ROT / 3 WEEK - 2 PILOTS - 90 FLT | 60000 |  |  | 30 jours x2 |  | 1000euros/rotation + 5000 par semaine
21
22 | SINGAPOUR - Official POC demonstration | 5000 |  |  | 5 jours x2
23 | Drop Plane (Mothership - Air Launch) | 60000
24 | Website | 2000
25 | Pilot Licence training program | 1000 |  | 5000
26 | Flight Club Structure | 1000
27 | ultimate seat
28 | Salary | 90000
29 | TOTAL | 493500
30
31
33 | Exowing Aero & Systems Design - JPW version P1000 | 20000 |  |  |  |  | demander a fred si on peut joindre structure epw et jpw
34 | Production jetwing system & engines | 110000 |  |  |  |  | (fuel tank 20000, fuel systems, electronics, pylon, engine p1000 x2)
32 | Prototype Exowing JPW#1 production - version P1000 | 7000
35 | Prototype Exowing JPW#1 Tunnel Tests | 10000 |  |  | 1000 x 2 = 2000
36 | Prototype Exowing JPW#1 1st Flight Tests - 10 FLT / 1 WEEK | 15000 |  |  | 2000 x 2 = 4000 |  | 1000euros/rotation + 5000 par semaine
37 | JPW#1 Flight tests campaign #1 - 45 ROT / 3 WEEK - 2 PILOTS - 90 FLT | 60000 |  |  | 5000 x 2 = 10000 |  | 1000euros/rotation + 5000 par semaine
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60